## Activities
Life-Cycle Phase / Engagement Objectives | Stakeholder Class
| Dormant | Discretionary | Demanding | Dominant | Dependent | Dangerous | Definitive
Initiating
Communicate information | N/A - no need to wake them up yet | Reports and memos to keep them informed and prevent creating urgency | Reports and memos to keep them feeling important | Meetings providing executive-level information to create foundations for Urgency if needed later | Reports and memos to keep them informed about meeting their needs | N/A - keep them in the dark as long as possible | Presentations, reports, briefings etc. based on individual preferences of receiving information
Obtain information | N/A - not holding anything important | Surveys, polls, questionnaires to understand them as group | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires for high-level information followed by meetings and interviews only when needed | N/A - they have no involvement, seeking information from them would only imply legitimacy | Workshops, brainstorming, meetings in small group or individual
Understand their needs and expectations | N/A - they typically have none | Surveys, polls, questionnaires to understand them as group | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires to understand their needs without investing too much time | Indirect influence, to understand thay they realy want without actually involving them | Workshops, brainstorming, meetings in small group or individual
Adjust expectations | N/A - none to start with | N/A - no power to enforce them anyway | N/A - none to start with | Indirect influence, as they typically listen only to a select number of advisors or peers | N/A - focus on those with power that dependent stakeholders coud try to influence | Indirect influence, as they typically listen only to peers with the same level of power | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Obtain support | N/A - not yet time to engage | N/A - no power to provide support | N/A - no real interest in the project | Meetings providing executive-level information to create foundations for Urgency if needed later | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Minimize potential negativity | N/A - not really having any opinion | Reports and memos to keep them informed and prevent creating urgency | N/A - no real interest in the project | Meetings and negotiations to address their issues if expressed | N/A - they don't have power to actually hurt the project | In-person meetings and negotiations to address their issues outside the project | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Get them actively involved | N/A - not yet time to engage | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get them actively involved (if needed at this time) | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Workshops, brainstorming, simulations for group decisions, presentations and briefing notes for individual decision
Obtain guidance | N/A - not yet time to engage | N/A - no power to enforce their opinion anyway | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires to understand their high-level objectives | N/A - would only imply legitimacy | Briefings if official direction is needed, informal discussions to "pick their brain"
Secure approvals | N/A - not on the approval list | N/A - not on the approval list | N/A - not on the approval list | In-person briefings to address any individual concerns | N/A - no power to approve | N/A - not part of the approval list | Meetings, presentations, reports, memos, briefing notes, informal discussions, indirect influence etc. as suitable for each stakeholder
Planning
Communicate information | Reports and briefing notes indicating that all is good to keep them dormant | Reports and memos to keep them informed and prevent a movement toward dependent | Reports and memos to keep them informed and prevent a movement toward dependent | Reports and briefing notes providing executive-level status | Reports and memos to keep them informed about meeting their needs | N/A - they have no involvement, sending them information would only imply legitimacy | Presentations, reports, briefings etc. based on individual preferences of receiving information
Obtain information | N/A - not holding anything important | Surveys, polls, questionnaires to understand them as group | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires for high-level information followed by meetings and interviews only when needed | N/A - they have no involvement, seeking information from them would only imply legitimacy | Workshops, brainstorming, meetings in small group or individual
Understand their needs and expectations | N/A - they typically have none | Surveys, polls, questionnaires to understand them as group | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires to understand their needs without investing too much time | Indirect influence, to understand thay they realy want without actually involving them | Workshops, brainstorming, meetings in small group or individual
Adjust expectations | N/A - none to start with | N/A - no power to enforce them anyway | N/A - none to start with | Indirect influence, as they typically listen only to a select number of advisors or peers | N/A - focus on those with power that dependent stakeholders coud try to influence | Indirect influence, as they typically listen only to peers with the same level of power | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Obtain support | Indirect influence and informal discussions to move them toward dominant | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get them actively involved | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Minimize potential negativity | N/A - not really having any opinion | Presentations and reports to prevent them feeling unsettled | N/A - no real interest in the project | In-person meetings and negotiations to address their issues | N/A - they don't have power to actually hurt the project | In-person meetings and negotiations to address their issues outside the project | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Get them actively involved | N/A - unless you need additional support to counter another powerful stakeholder | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get theim actively involved | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Workshops, brainstorming, simulations for group decisions, presentations and briefing notes for individual decision
Obtain guidance | Interviews to feel valued and prevent from moving toward dangerous | N/A - no power to enforce their opinion anyway | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires to understand their high-level objectives | N/A - would only imply legitimacy | Briefings if official direction is needed, informal discussions to "pick their brain"
Secure approvals | N/A - not on the approval list | N/A - not on the approval list | N/A - not on the approval list | In-person briefings to address any individual concerns | N/A - no power to approve | N/A - not part of the approval list | Meetings, presentations, reports, memos, briefing notes, informal discussions, indirect influence etc. as suitable for each stakeholder
Executing
Communicate information | Reports and briefing notes indicating that all is good to keep them dormant | Reports and memos to keep them informed and prevent a movement toward dependent | Reports and memos to keep them informed and prevent a movement toward dependent | Reports and briefing notes providing executive-level status | Reports and memos to keep them informed about meeting their needs | N/A - they have no involvement, sending them information would only imply legitimacy | Presentations, reports, briefings etc. to keep them informed of progress
Obtain information | N/A - not holding anything important | N/A - all information should have been obtained during Planning | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires for high-level information followed by meetings and interviews only when needed | N/A - they have no involvement, seeking information from them would only imply legitimacy | Workshops, brainstorming, meetings in small group or individual
Understand their needs and expectations | N/A - they typically have none | N/A - all information should have been obtained during Planning | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires to understand their needs without investing too much time | Indirect influence, to understand thay they realy want without actually involving them | Workshops, brainstorming, meetings in small group or individual
Adjust expectations | N/A - none to start with | N/A - no power to enforce them anyway | N/A - none to start with | Indirect influence, as they typically listen only to a select number of advisors or peers | N/A - focus on those with power that dependent stakeholders coud try to influence | Indirect influence, as they typically listen only to peers with the same level of power | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Obtain support | Indirect influence and informal discussions to move them toward dominant | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get theim actively involved | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Presentations, briefing notes and memos to make them feel part of decision-making
Minimize potential negativity | N/A - not really having any opinion | Reports to prevent them feeling unsettled | N/A - no real interest in the project | In-person meetings and negotiations to address their issues | N/A - they don't have power to actually hurt the project | In-person meetings and negotiations to address their issues outside the project | Presentations, briefing notes and memos to make them feel part of decision-making
Get them actively involved | N/A - unless you need additional support to counter another powerful stakeholder | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get them actively involved | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Workshops, brainstorming, simulations for group decisions, presentations and briefing notes for individual decision
Obtain guidance | Interviews to feel valued and prevent from moving toward dangerous | N/A - no power to enforce their opinion anyway | N/A - no real interest in the project | Interviews, individual or small group, to provide them the attention they deserve | Surveys, polls, questionnaires to understand their high-level objectives | N/A - would only imply legitimacy | Briefings if official direction is needed, informal discussions to "pick their brain"
Secure approvals | N/A - not on the approval list | N/A - not on the approval list | N/A - not on the approval list | In-person briefings to address any individual concerns | N/A - no power to approve | N/A - not part of the approval list | Meetings, presentations, reports, memos, briefing notes, informal discussions, indirect influence etc. as suitable for each stakeholder
Acceptance
Communicate information | N/A - nothing needed from them at this time | N/A - nothing needed from them at this time | N/A - if they hear about approvals will want to be part of it | Reports and briefing notes providing executive-level status | Reports and memos to keep them informed about meeting their needs | N/A - if they hear about approvals will want to be part of it | Presentations, reports, briefings etc. based on individual preferences of receiving information
Obtain information | N/A - not holding anything important | N/A - if not done already it's too late | N/A - no real interest in the project | Interviews, individual or small group, to understand any concerns they may have | N/A - if not done already it's too late | N/A - if they hear about approvals will want to be part of it | Workshops, brainstorming, meetings in small group or individual to understand any concerns they may have
Understand their needs and expectations | N/A - they typically have none | N/A - if not done already it's too late | N/A - no real interest in the project | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late
Adjust expectations | N/A - none to start with | N/A - no power to enforce them anyway | N/A - none to start with | Indirect influence, as they typically listen only to a select number of advisors or peers | N/A - focus on those with power that dependent stakeholders coud try to influence | Indirect influence, as they typically listen only to peers with the same level of power | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Obtain support | Indirect influence and informal discussions to move them toward dominant if needed to influence others | N/A - no power to provide support | N/A - no real interest in the project | Indirect influence, as they typically listen only to a select number of advisors or peers | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Minimize potential negativity | N/A - not really having any opinion | N/A - no power to enforce their opinion anyway | N/A - no real interest in the project | In-person meetings and negotiations to address their issues | N/A - they don't have power to actually hurt the project | In-person meetings and negotiations to address their issues outside the project | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Get them actively involved | N/A - unless you need additional support to counter another powerful stakeholder | N/A - no power to provide support | N/A - no real interest in the project | N/A - if not done already it's too late | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Workshops, brainstorming, simulations for group decisions, presentations and briefing notes for individual decision
Obtain guidance | N/A - not on the approval list | N/A - no power to enforce their opinion anyway | N/A - no real interest in the project | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - would only imply legitimacy | Briefings if official direction is needed, informal discussions to "pick their brain"
Secure approvals | N/A - not on the approval list | N/A - not on the approval list | N/A - not on the approval list | In-person briefings to address any individual concerns | N/A - no power to approve | N/A - not part of the approval list | Meetings, presentations, reports, memos, briefing notes, informal discussions, indirect influence etc. as suitable for each stakeholder
Transition
Communicate information | Reports and briefing notes indicating what is coming up | Reports and memos to keep them informed that their needs are being met | Reports and memos to keep them informed and feeling "in the know" | Reports and briefing notes providing a preview of "things to come" | Reports and memos to keep them informed about meeting their needs | Reports and briefing notes providing a preview of "things to come" | Presentations, reports, briefings etc. based on individual preferences of receiving information
Obtain information | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late
Understand their needs and expectations | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late
Adjust expectations | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late
Obtain support | Reports and briefing notes indicating what is coming up and how it's good for them | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get them actively involved | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Minimize potential negativity | N/A - not really having any opinion | Presentations and reports to prevent them feeling unsettled | N/A - no real interest in the project | In-person meetings and negotiations to address their issues | N/A - they don't have power to actually hurt the project | In-person meetings and negotiations to address their issues outside the project | Negotiations when possible, indirect influence when there is limited access to that stakeholder
Get them actively involved | N/A - unless you need additional support to counter another powerful stakeholder | N/A - no power to provide support | N/A - no real interest in the project | Negotiations to provide an incentive to get theim actively involved | N/A - they don't have power to actually support the project | In-person meetings if there is any chance to obtain legitimacy and become a definitive stakeholder | Workshops, brainstorming, simulations for group decisions, presentations and briefing notes for individual decision
Obtain guidance | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late | N/A - if not done already it's too late
Secure approvals | N/A - not on the approval list | N/A - not on the approval list | N/A - not on the approval list | In-person briefings to address any individual concerns | N/A - no power to approve | N/A - not part of the approval list | Reports, memos, briefing notes, informal discussions, indirect influence etc. as suitable for each stakeholder